## Slide 1
QA Release | Duration | Scope
NCI QA - 1.0 RC1 | April 20 – June 22 | a. JAXB CDA Corruption Issue b. Semantic Adapter Security using SSL c. Error Handling Defect Fixes (5) d. Deployment Guide Updates e. Admin Guide Updates
NCI QA - 1.0 MR1 | June 26 – June 29 June 27 – July 13 | Fixes to RC1 bugs
NCI QA – 1.0 MR2 | July 5 – July 18 July 16 – July 27 July 16 - Aug 10 | Security Administration module, SFTP Support
NCI QA – 1.0 MR3 | Sep 4 – Sep 17 | Fixes to MR2 bugs, CDW Asynchronous Load, App Scan, 508 Compliance
NCI QA – 1.0 MR4 | Oct 8 – Oct 19 | Fixes to MR3 bugs, caCIS - Epic Integration
NCI QA - 1.0 RC2 | Oct 29 – Nov 2 | Fixes to MR4 bugs
NCI DEV – 1.0 RC2 | Dec 7 – Jan 7 | E2E Development Testing with THE.Force (CDA documents generated by THE.Force Semantic Adapter)
Integration QA | Jan 7 – Feb 7 | THE Force – caCIS Integration, UCSF – Epic Integration QA
UAT – 1.0 | Feb 1 – Feb 28 | 
caCIS – QA - Planned and Actual Dates
This plan will be revisited periodically and adjusted according to 2TRANSCEND plan updates.