## Sheet1
Priority | Category | Sequence | Task | Notes
2 | Design Data Warehouse | 1 | Design query architecture for data warehouse to support multiple query languages & enforcement of access restrictions
2 | Design Data Warehouse | 2 | Define data warehouse repository format, including minimal optimizations
2 | Design Data Warehouse | 3 | Define ad-hoc query services interface on data warehouse (including multiple query languages)
2 | Design Data Warehouse | 4 | Design mechanism for CQL queries
2 | Design Data Warehouse | 4 | Design mechanism for XQuery queries
2 | Design Data Warehouse | 5 | Complete ECCF documentation (CIM + PIM) for Warehouse interfaces (Adhoc Query)
2 | Design Data Warehouse | 5 | Define ETL process between IPs (Clinical Repositories) and Data Warehouse
3 | Design Data Warehouse |  | Define ETL interface from Data Warehouse to Data marts
1 | Design IP |  | Define "configuration" files for IP - Document generation configuration (what sections, what transform, what doc type), document transmission config (what type, what recipients, what transfer mechanism)
1 | Design IP |  | Define clinical repository format (section data, document definition data)
1 | Design IP |  | Define internal interfaces (Document Generator, Canonical Model Processor, Clinical Repository, Query Processor)
1 | Design IP |  | Define key services interface between SA and IP (StoreCanonicalData, AcceptCanonicalData, DeleteCanonicalData)
1 | Design IP |  | Define security interface for SA to/from IP (including authorization on IP side)
1 | Design IP |  | Define security interface for XDS to "external" (Query, Get) (system & user authentication, authorization)
1 | Design IP |  | Document caCIS-specific constraints & extensions on IHE interfaces
1 | Design IP |  | IP Choreography to respond to AcceptCanonicalData
1 | Design IP |  | IP Choreography to respond to XDS-Get
1 | Design IP |  | IP Choreography to respond to XDS-NAV (receiver side)
2 | Design IP |  | Complete ECCF documentation (CIM + PIM) for IP external interfaces (XDS Get, XDS Query, XDS NAV, Secure e-mail, Secure FTP)
2 | Design IP |  | Define data deletion policy for Clinical Repository
2 | Design IP |  | IP Choreography to respond to Delete Canonical
2 | Design IP |  | IP Choreography to respond to XDS-Query
1 | Design SA |  | Define key services interface between SA and IP (StoreCanonicalData)
1 | Design SA |  | Define security interface for Tolven (TRANSCEND & PCO) to SA (just mutual authentication) | Includes PCO user security
1 | Design SA |  | SA Choreography for Canonical to TRIM from StoreCanonical
1 | Design SA |  | SA Choreography for TRIM to Canonical and invoke AcceptCanonical
2 | Design SA |  | Complete ECCF documentation (CIM + PIM) for SA interfaces
2 | Design SA |  | Define additional services interface between SA and IP (PullCanonicalData)
2 | Design SA |  | Design identity resolver façade interface
2 | Design SA |  | Determine existing interface with identity resolver
1 | Mappings |  | Define canonical format via Implementation Guide
1 | Mappings |  | Define IG for PCO exchange
1 | Mappings |  | Define IG for EPIC copy/paste exchange CDA
1 | Mappings |  | Define mapping from Canonical to/from EPIC copy/paste exchange CDA
1 | Mappings |  | Define mapping from Canonical to/from PCO exchange CDA
1 | Mappings |  | Define mapping from PCO TRIM to/from Canonical
1 | Mappings |  | Define mapping from TRANSCEND to Canonical
2 | Mappings |  | Define IG for Full CDA
2 | Mappings |  | Define IG for HL7
2 | Mappings |  | Define IG for XML ITS
2 | Mappings |  | Define mapping from Cannonical to HL7
2 | Mappings |  | Define mapping from Cannonical to/from XML ITS
2 | Mappings |  | Define mapping from Canonical to CCD
2 | Mappings |  | Define mapping from Canonical to Full CDA
1 | PCO |  | Define integration rules for PCO data
1 | PCO |  | Define PCO RMIM
1 | PCO |  | Define Tolven workflow between SA and PCO (importing data, exporting data)
3 | PCO |  | Define PCO GUI wireframes
? | PCO |  | Integrate caGRID security into Tolven PCO application
1 | Security |  | Define logging policy and log format
1 | TRANSCEND |  | Discuss & Confirm Tolven workflow from TRANSCEND to SA (bulk export, PCO export, EPIC export)
Note on A1: Lloyd McKenzie: 1 = must do for core objectives of PCO and TRANSCEND communication 2 = Should do for "complete' solution 3 = Time allowing